## Construction Schedule
WBS | Task Name | Phase | Discipline | Storey | Quantity | UOM | Productivity | Duration (days) | Start Date | Finish Date | Labor Resource | Crew Size | Equipment | Status | % Complete
1.2.1 | Ground - Install Column (STR) | Superstructure | STR | Ground | 4 | EA | 6 | 1 | 2025-01-16T00:00:00 | 2025-01-17T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.2.17 | Roof - Install Column (STR) | Superstructure | STR | Roof | 8 | EA | 6 | 1.3333 | 2025-01-16T00:00:00 | 2025-01-18T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.2.123 | Typical_F2 - Install Column (STR) | Superstructure | STR | Typical_F2 | 6 | EA | 6 | 1 | 2025-01-16T00:00:00 | 2025-01-17T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.4.10 | Ground - Install Slab (STR) | Superstructure | STR | Ground | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.24 | Roof - Install Slab (STR) | Superstructure | STR | Roof | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.35 | Typical_F10 - Install Slab (STR) | Superstructure | STR | Typical_F10 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.47 | Typical_F11 - Install Slab (STR) | Superstructure | STR | Typical_F11 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.59 | Typical_F12 - Install Slab (STR) | Superstructure | STR | Typical_F12 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.71 | Typical_F13 - Install Slab (STR) | Superstructure | STR | Typical_F13 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.83 | Typical_F14 - Install Slab (STR) | Superstructure | STR | Typical_F14 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.95 | Typical_F15 - Install Slab (STR) | Superstructure | STR | Typical_F15 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.107 | Typical_F16 - Install Slab (STR) | Superstructure | STR | Typical_F16 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.119 | Typical_F17 - Install Slab (STR) | Superstructure | STR | Typical_F17 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.132 | Typical_F2 - Install Slab (STR) | Superstructure | STR | Typical_F2 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.144 | Typical_F3 - Install Slab (STR) | Superstructure | STR | Typical_F3 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.156 | Typical_F4 - Install Slab (STR) | Superstructure | STR | Typical_F4 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.168 | Typical_F5 - Install Slab (STR) | Superstructure | STR | Typical_F5 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.180 | Typical_F6 - Install Slab (STR) | Superstructure | STR | Typical_F6 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.192 | Typical_F7 - Install Slab (STR) | Superstructure | STR | Typical_F7 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.204 | Typical_F8 - Install Slab (STR) | Superstructure | STR | Typical_F8 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.216 | Typical_F9 - Install Slab (STR) | Superstructure | STR | Typical_F9 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.5.8 | Ground - Install PipeSegment (FP) | MEP Rough-in | FP | Ground | 39 | EA | 25 | 1.56 | 2025-01-31T00:00:00 | 2025-02-02T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.21 | Roof - Install PipeSegment (FP) | MEP Rough-in | FP | Roof | 4 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.33 | Typical_F10 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F10 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.45 | Typical_F11 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F11 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.57 | Typical_F12 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F12 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.69 | Typical_F13 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F13 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.81 | Typical_F14 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F14 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.93 | Typical_F15 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F15 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.105 | Typical_F16 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F16 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.117 | Typical_F17 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F17 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.130 | Typical_F2 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F2 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.142 | Typical_F3 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F3 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.154 | Typical_F4 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F4 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.166 | Typical_F5 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F5 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.178 | Typical_F6 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F6 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.190 | Typical_F7 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F7 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.202 | Typical_F8 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F8 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.214 | Typical_F9 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F9 | 9 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.7.2 | Ground - Install Door (ARC) | Architecture | ARC | Ground | 9 | EA | 5 | 1.8 | 2025-02-10T00:00:00 | 2025-02-12T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.13 | Ground - Install StairFlight (ARC) | Architecture | ARC | Ground | 2 | EA | 2 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.15 | Ground - Install Window (ARC) | Architecture | ARC | Ground | 10 | EA | 5 | 2 | 2025-02-10T00:00:00 | 2025-02-12T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.18 | Roof - Install Door (ARC) | Architecture | ARC | Roof | 2 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.27 | Typical_F10 - Install Door (ARC) | Architecture | ARC | Typical_F10 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.39 | Typical_F11 - Install Door (ARC) | Architecture | ARC | Typical_F11 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.51 | Typical_F12 - Install Door (ARC) | Architecture | ARC | Typical_F12 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.63 | Typical_F13 - Install Door (ARC) | Architecture | ARC | Typical_F13 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.75 | Typical_F14 - Install Door (ARC) | Architecture | ARC | Typical_F14 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.87 | Typical_F15 - Install Door (ARC) | Architecture | ARC | Typical_F15 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.99 | Typical_F16 - Install Door (ARC) | Architecture | ARC | Typical_F16 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.111 | Typical_F17 - Install Door (ARC) | Architecture | ARC | Typical_F17 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.124 | Typical_F2 - Install Door (ARC) | Architecture | ARC | Typical_F2 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.136 | Typical_F3 - Install Door (ARC) | Architecture | ARC | Typical_F3 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.148 | Typical_F4 - Install Door (ARC) | Architecture | ARC | Typical_F4 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.160 | Typical_F5 - Install Door (ARC) | Architecture | ARC | Typical_F5 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.172 | Typical_F6 - Install Door (ARC) | Architecture | ARC | Typical_F6 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.184 | Typical_F7 - Install Door (ARC) | Architecture | ARC | Typical_F7 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.196 | Typical_F8 - Install Door (ARC) | Architecture | ARC | Typical_F8 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.208 | Typical_F9 - Install Door (ARC) | Architecture | ARC | Typical_F9 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.8.23 | Roof - Install Roof (ARC) | Architecture | ARC | Roof | 1 | EA | 25 | 1 | 2025-02-15T00:00:00 | 2025-02-16T00:00:00 | ROOFER | 2 |  | Not Started | 0
1.9.5 | Ground - Install LightFixture (ELEC) | MEP Final | ELEC | Ground | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.7 | Ground - Install Outlet (ELEC) | MEP Final | ELEC | Ground | 6 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.30 | Typical_F10 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F10 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.32 | Typical_F10 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F10 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.42 | Typical_F11 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F11 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.44 | Typical_F11 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F11 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.54 | Typical_F12 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F12 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.56 | Typical_F12 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F12 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.66 | Typical_F13 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F13 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.68 | Typical_F13 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F13 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.78 | Typical_F14 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F14 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.80 | Typical_F14 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F14 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.90 | Typical_F15 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F15 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.92 | Typical_F15 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F15 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.102 | Typical_F16 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F16 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.104 | Typical_F16 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F16 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.114 | Typical_F17 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F17 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.116 | Typical_F17 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F17 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.127 | Typical_F2 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F2 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.129 | Typical_F2 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F2 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.139 | Typical_F3 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F3 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.141 | Typical_F3 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F3 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.151 | Typical_F4 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F4 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.153 | Typical_F4 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F4 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.163 | Typical_F5 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F5 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.165 | Typical_F5 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F5 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.175 | Typical_F6 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F6 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.177 | Typical_F6 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F6 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.187 | Typical_F7 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F7 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.189 | Typical_F7 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F7 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.199 | Typical_F8 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F8 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.201 | Typical_F8 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F8 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.211 | Typical_F9 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F9 | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.213 | Typical_F9 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F9 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.11.4 | Ground - Install Furniture (ARC) | Finishes | ARC | Ground | 17 | EA | 8 | 2.125 | 2025-03-02T00:00:00 | 2025-03-06T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.29 | Typical_F10 - Install Furniture (ARC) | Finishes | ARC | Typical_F10 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.41 | Typical_F11 - Install Furniture (ARC) | Finishes | ARC | Typical_F11 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.53 | Typical_F12 - Install Furniture (ARC) | Finishes | ARC | Typical_F12 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.65 | Typical_F13 - Install Furniture (ARC) | Finishes | ARC | Typical_F13 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.77 | Typical_F14 - Install Furniture (ARC) | Finishes | ARC | Typical_F14 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.89 | Typical_F15 - Install Furniture (ARC) | Finishes | ARC | Typical_F15 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.101 | Typical_F16 - Install Furniture (ARC) | Finishes | ARC | Typical_F16 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.113 | Typical_F17 - Install Furniture (ARC) | Finishes | ARC | Typical_F17 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.126 | Typical_F2 - Install Furniture (ARC) | Finishes | ARC | Typical_F2 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.138 | Typical_F3 - Install Furniture (ARC) | Finishes | ARC | Typical_F3 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.150 | Typical_F4 - Install Furniture (ARC) | Finishes | ARC | Typical_F4 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.162 | Typical_F5 - Install Furniture (ARC) | Finishes | ARC | Typical_F5 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.174 | Typical_F6 - Install Furniture (ARC) | Finishes | ARC | Typical_F6 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.186 | Typical_F7 - Install Furniture (ARC) | Finishes | ARC | Typical_F7 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.198 | Typical_F8 - Install Furniture (ARC) | Finishes | ARC | Typical_F8 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.210 | Typical_F9 - Install Furniture (ARC) | Finishes | ARC | Typical_F9 | 5 | EA | 8 | 1 | 2025-03-02T00:00:00 | 2025-03-04T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.99.0 | Ground - Install AirTerminal (ACMV) | Unknown | ACMV | Ground | 61 | EA | 10 | 6.1 | 2026-05-16T00:00:00 | 2026-05-24T00:00:00 |  | 2 |  | Not Started | 0
1.99.3 | Ground - Install FireSuppressionTerminal (FP) | Unknown | FP | Ground | 19 | EA | 10 | 1.9 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.6 | Ground - Install Member (STR) | Unknown | STR | Ground | 99 | EA | 10 | 9.9 | 2026-05-16T00:00:00 | 2026-05-28T00:00:00 |  | 2 |  | Not Started | 0
1.99.9 | Ground - Install Plate (ARC) | Unknown | ARC | Ground | 27 | EA | 10 | 2.7 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.11 | Ground - Install Space (STR) | Unknown | STR | Ground | 8 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.12 | Ground - Install Stair (STR) | Unknown | STR | Ground | 2 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.14 | Ground - Install SwitchingDevice (ELEC) | Unknown | ELEC | Ground | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.16 | Roof - Install AirTerminal (ACMV) | Unknown | ACMV | Roof | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.19 | Roof - Install FireSuppressionTerminal (FP) | Unknown | FP | Roof | 4 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.20 | Roof - Install Member (STR) | Unknown | STR | Roof | 22 | EA | 10 | 2.2 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.22 | Roof - Install Plate (ARC) | Unknown | ARC | Roof | 8 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.25 | Roof - Install Space (STR) | Unknown | STR | Roof | 4 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.26 | Typical_F10 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F10 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.28 | Typical_F10 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F10 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.31 | Typical_F10 - Install Member (STR) | Unknown | STR | Typical_F10 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.34 | Typical_F10 - Install Plate (ARC) | Unknown | ARC | Typical_F10 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.36 | Typical_F10 - Install Space (STR) | Unknown | STR | Typical_F10 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.37 | Typical_F10 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F10 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.38 | Typical_F11 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F11 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.40 | Typical_F11 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F11 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.43 | Typical_F11 - Install Member (STR) | Unknown | STR | Typical_F11 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.46 | Typical_F11 - Install Plate (ARC) | Unknown | ARC | Typical_F11 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.48 | Typical_F11 - Install Space (STR) | Unknown | STR | Typical_F11 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.49 | Typical_F11 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F11 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.50 | Typical_F12 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F12 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.52 | Typical_F12 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F12 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.55 | Typical_F12 - Install Member (STR) | Unknown | STR | Typical_F12 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.58 | Typical_F12 - Install Plate (ARC) | Unknown | ARC | Typical_F12 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.60 | Typical_F12 - Install Space (STR) | Unknown | STR | Typical_F12 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.61 | Typical_F12 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F12 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.62 | Typical_F13 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F13 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.64 | Typical_F13 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F13 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.67 | Typical_F13 - Install Member (STR) | Unknown | STR | Typical_F13 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.70 | Typical_F13 - Install Plate (ARC) | Unknown | ARC | Typical_F13 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.72 | Typical_F13 - Install Space (STR) | Unknown | STR | Typical_F13 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.73 | Typical_F13 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F13 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.74 | Typical_F14 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F14 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.76 | Typical_F14 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F14 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.79 | Typical_F14 - Install Member (STR) | Unknown | STR | Typical_F14 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.82 | Typical_F14 - Install Plate (ARC) | Unknown | ARC | Typical_F14 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.84 | Typical_F14 - Install Space (STR) | Unknown | STR | Typical_F14 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.85 | Typical_F14 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F14 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.86 | Typical_F15 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F15 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.88 | Typical_F15 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F15 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.91 | Typical_F15 - Install Member (STR) | Unknown | STR | Typical_F15 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.94 | Typical_F15 - Install Plate (ARC) | Unknown | ARC | Typical_F15 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.96 | Typical_F15 - Install Space (STR) | Unknown | STR | Typical_F15 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.97 | Typical_F15 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F15 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.98 | Typical_F16 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F16 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.100 | Typical_F16 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F16 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.103 | Typical_F16 - Install Member (STR) | Unknown | STR | Typical_F16 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.106 | Typical_F16 - Install Plate (ARC) | Unknown | ARC | Typical_F16 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.108 | Typical_F16 - Install Space (STR) | Unknown | STR | Typical_F16 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.109 | Typical_F16 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F16 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.110 | Typical_F17 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F17 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.112 | Typical_F17 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F17 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.115 | Typical_F17 - Install Member (STR) | Unknown | STR | Typical_F17 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.118 | Typical_F17 - Install Plate (ARC) | Unknown | ARC | Typical_F17 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.120 | Typical_F17 - Install Space (STR) | Unknown | STR | Typical_F17 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.121 | Typical_F17 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F17 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.122 | Typical_F2 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F2 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.125 | Typical_F2 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F2 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.128 | Typical_F2 - Install Member (STR) | Unknown | STR | Typical_F2 | 32 | EA | 10 | 3.2 | 2026-05-16T00:00:00 | 2026-05-21T00:00:00 |  | 2 |  | Not Started | 0
1.99.131 | Typical_F2 - Install Plate (ARC) | Unknown | ARC | Typical_F2 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.133 | Typical_F2 - Install Space (STR) | Unknown | STR | Typical_F2 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.134 | Typical_F2 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F2 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.135 | Typical_F3 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F3 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.137 | Typical_F3 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F3 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.140 | Typical_F3 - Install Member (STR) | Unknown | STR | Typical_F3 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.143 | Typical_F3 - Install Plate (ARC) | Unknown | ARC | Typical_F3 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.145 | Typical_F3 - Install Space (STR) | Unknown | STR | Typical_F3 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.146 | Typical_F3 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F3 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.147 | Typical_F4 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F4 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.149 | Typical_F4 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F4 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.152 | Typical_F4 - Install Member (STR) | Unknown | STR | Typical_F4 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.155 | Typical_F4 - Install Plate (ARC) | Unknown | ARC | Typical_F4 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.157 | Typical_F4 - Install Space (STR) | Unknown | STR | Typical_F4 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.158 | Typical_F4 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F4 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.159 | Typical_F5 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F5 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.161 | Typical_F5 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F5 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.164 | Typical_F5 - Install Member (STR) | Unknown | STR | Typical_F5 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.167 | Typical_F5 - Install Plate (ARC) | Unknown | ARC | Typical_F5 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.169 | Typical_F5 - Install Space (STR) | Unknown | STR | Typical_F5 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.170 | Typical_F5 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F5 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.171 | Typical_F6 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F6 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.173 | Typical_F6 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F6 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.176 | Typical_F6 - Install Member (STR) | Unknown | STR | Typical_F6 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.179 | Typical_F6 - Install Plate (ARC) | Unknown | ARC | Typical_F6 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.181 | Typical_F6 - Install Space (STR) | Unknown | STR | Typical_F6 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.182 | Typical_F6 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F6 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.183 | Typical_F7 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F7 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.185 | Typical_F7 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F7 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.188 | Typical_F7 - Install Member (STR) | Unknown | STR | Typical_F7 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.191 | Typical_F7 - Install Plate (ARC) | Unknown | ARC | Typical_F7 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.193 | Typical_F7 - Install Space (STR) | Unknown | STR | Typical_F7 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.194 | Typical_F7 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F7 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.195 | Typical_F8 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F8 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.197 | Typical_F8 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F8 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.200 | Typical_F8 - Install Member (STR) | Unknown | STR | Typical_F8 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.203 | Typical_F8 - Install Plate (ARC) | Unknown | ARC | Typical_F8 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.205 | Typical_F8 - Install Space (STR) | Unknown | STR | Typical_F8 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.206 | Typical_F8 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F8 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.207 | Typical_F9 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F9 | 12 | EA | 10 | 1.2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.209 | Typical_F9 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F9 | 7 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.212 | Typical_F9 - Install Member (STR) | Unknown | STR | Typical_F9 | 30 | EA | 10 | 3 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.215 | Typical_F9 - Install Plate (ARC) | Unknown | ARC | Typical_F9 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.217 | Typical_F9 - Install Space (STR) | Unknown | STR | Typical_F9 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.218 | Typical_F9 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F9 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0

## Project Summary
Terminal 1 Construction
Database | condo_mid.db
Total Tasks | 219
Project Start | 2025-01-16T00:00:00
Project Finish | 2026-05-17T00:00:00
Total Duration | 487 days
Generated | 2026-02-06 23:03:48
Phase Summary | Task Count
Architecture | 21
Finishes | 17
MEP Final | 34
MEP Rough-in | 18
Superstructure | 21
Unknown | 108
Discipline Summary | Task Count
ACMV | 18
ARC | 56
ELEC | 51
FP | 36
STR | 58

## BIM 5D Dashboard
Terminal 1 Construction - BIM 5D Analytics Dashboard
Phase Duration Analysis
Phase | Total Days
Unknown | 166.2
MEP Final | 34
Architecture | 22.8
Superstructure | 21.33
MEP Rough-in | 18.56
Finishes | 18.12
Resource Workload Analysis
Phase | Total Man-Days
Unknown | 332.4
Superstructure | 121.3
MEP Final | 68
Architecture | 45.6
MEP Rough-in | 37.1
Finishes | 36.2
S-Curve Progress Analysis
Week | Cumulative %
W0 | 0
W3 | 17.8
W6 | 42.9
W9 | 50.7
W12 | 50.7
W15 | 50.7
W18 | 50.7
W21 | 50.7
W24 | 50.7
W27 | 50.7
W30 | 50.7
W33 | 50.7
W36 | 50.7
W39 | 50.7
W42 | 50.7
W45 | 50.7
W48 | 50.7
W51 | 50.7
W54 | 50.7
W57 | 50.7
W60 | 50.7
W63 | 50.7
W66 | 50.7
Milestone Timeline | 50.7
Milestone | Day Offset | Date
🏁 Project Start | 0 | 2025-01-16T00:00:00
▶ Superstructure Start | 0 | 2025-01-16T00:00:00
◀ Superstructure End | 12 | 2025-01-28T00:00:00
▶ MEP Rough-in Start | 15 | 2025-01-31T00:00:00
◀ MEP Rough-in End | 17 | 2025-02-02T00:00:00
▶ Architecture Start | 25 | 2025-02-10T00:00:00
◀ Architecture End | 31 | 2025-02-16T00:00:00
▶ MEP Final Start | 35 | 2025-02-20T00:00:00
◀ MEP Final End | 36 | 2025-02-21T00:00:00
▶ Finishes Start | 45 | 2025-03-02T00:00:00
◀ Finishes End | 49 | 2025-03-06T00:00:00
▶ Unknown Start | 485 | 2026-05-16T00:00:00
🏁 Project Finish | 486 | 2026-05-17T00:00:00
◀ Unknown End | 497 | 2026-05-28T00:00:00
Gantt Timeline (Strategic Tasks by Phase)
Task | Phase | Start (Day) | Duration (Days)
Roof - Install Column (STR) | Superstructure | 0 | 1.3
Ground - Install PipeSegment (FP) | MEP Rough-in | 15 | 1.6
Ground - Install Window (ARC) | Architecture | 25 | 2
Ground - Install LightFixture (ELEC | MEP Final | 35 | 1
Ground - Install Furniture (ARC) | Finishes | 45 | 2.1
Ground - Install Member (STR) | Unknown | 485 | 9.9
Ground - Install AirTerminal (ACMV) | Unknown | 485 | 6.1
Typical_F2 - Install Member (STR) | Unknown | 485 | 3.2
Typical_F10 - Install Member (STR) | Unknown | 485 | 3
Typical_F11 - Install Member (STR) | Unknown | 485 | 3