## Construction Schedule
WBS | Task Name | Phase | Discipline | Storey | Quantity | UOM | Productivity | Duration (days) | Start Date | Finish Date | Labor Resource | Crew Size | Equipment | Status | % Complete
1.3.0 | Level 1 - Install Beam (STR) | Superstructure | STR | Level 1 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.9 | Level 2 - Install Beam (STR) | Superstructure | STR | Level 2 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.4.6 | Level 1 - Install Slab (ARC) | Superstructure | ARC | Level 1 | 10 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.15 | Level 2 - Install Slab (ARC) | Superstructure | ARC | Level 2 | 10 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.25 | Unknown - Install Slab (ARC) | Superstructure | ARC | Unknown | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.6.7 | Level 1 - Install Wall (ARC) | Architecture | ARC | Level 1 | 21 | EA | 12 | 1.75 | 2025-02-05T00:00:00 | 2025-02-07T00:00:00 | MASON | 3 |  | Not Started | 0
1.6.16 | Level 2 - Install Wall (ARC) | Architecture | ARC | Level 2 | 25 | EA | 12 | 2.0833 | 2025-02-05T00:00:00 | 2025-02-08T00:00:00 | MASON | 3 |  | Not Started | 0
1.6.20 | Roof - Install Wall (ARC) | Architecture | ARC | Roof | 4 | EA | 12 | 1 | 2025-02-05T00:00:00 | 2025-02-06T00:00:00 | MASON | 3 |  | Not Started | 0
1.6.22 | T/FDN - Install Wall (ARC) | Architecture | ARC | T/FDN | 7 | EA | 12 | 1 | 2025-02-05T00:00:00 | 2025-02-06T00:00:00 | MASON | 3 |  | Not Started | 0
1.7.1 | Level 1 - Install Door (ARC) | Architecture | ARC | Level 1 | 6 | EA | 5 | 1.2 | 2025-02-10T00:00:00 | 2025-02-12T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.8 | Level 1 - Install Window (ARC) | Architecture | ARC | Level 1 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.10 | Level 2 - Install Door (ARC) | Architecture | ARC | Level 2 | 8 | EA | 5 | 1.6 | 2025-02-10T00:00:00 | 2025-02-12T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.17 | Level 2 - Install Window (ARC) | Architecture | ARC | Level 2 | 18 | EA | 5 | 3.6 | 2025-02-10T00:00:00 | 2025-02-14T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.21 | Roof - Install Window (ARC) | Architecture | ARC | Roof | 2 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.26 | Unknown - Install StairFlight (ARC) | Architecture | ARC | Unknown | 2 | EA | 2 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.9.4 | Level 1 - Install FlowTerminal (MEP) | MEP Final | MEP | Level 1 | 62 | EA | 10 | 6.2 | 2025-02-20T00:00:00 | 2025-02-28T00:00:00 | HVAC_TECH | 2 |  | Not Started | 0
1.9.13 | Level 2 - Install FlowTerminal (MEP) | MEP Final | MEP | Level 2 | 43 | EA | 10 | 4.3 | 2025-02-20T00:00:00 | 2025-02-26T00:00:00 | HVAC_TECH | 2 |  | Not Started | 0
1.99.2 | Level 1 - Install FlowFitting (MEP) | Unknown | MEP | Level 1 | 260 | EA | 10 | 26 | 2026-05-16T00:00:00 | 2026-06-16T00:00:00 |  | 2 |  | Not Started | 0
1.99.3 | Level 1 - Install FlowSegment (MEP) | Unknown | MEP | Level 1 | 163 | EA | 10 | 16.3 | 2026-05-16T00:00:00 | 2026-06-05T00:00:00 |  | 2 |  | Not Started | 0
1.99.5 | Level 1 - Install FurnishingElement (ARC) | Unknown | ARC | Level 1 | 41 | EA | 10 | 4.1 | 2026-05-16T00:00:00 | 2026-05-22T00:00:00 |  | 2 |  | Not Started | 0
1.99.11 | Level 2 - Install FlowFitting (MEP) | Unknown | MEP | Level 2 | 94 | EA | 10 | 9.4 | 2026-05-16T00:00:00 | 2026-05-28T00:00:00 |  | 2 |  | Not Started | 0
1.99.12 | Level 2 - Install FlowSegment (MEP) | Unknown | MEP | Level 2 | 263 | EA | 10 | 26.3 | 2026-05-16T00:00:00 | 2026-06-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.14 | Level 2 - Install FurnishingElement (ARC) | Unknown | ARC | Level 2 | 20 | EA | 10 | 2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.18 | Roof - Install FlowFitting (MEP) | Unknown | MEP | Roof | 4 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.19 | Roof - Install FlowSegment (MEP) | Unknown | MEP | Roof | 1 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.23 | Unknown - Install Member (STR) | Unknown | STR | Unknown | 4 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.24 | Unknown - Install Railing (ARC) | Unknown | ARC | Unknown | 4 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0

## Project Summary
Terminal 1 Construction
Database | ifc2x3_duplex.db
Total Tasks | 27
Project Start | 2025-01-21T00:00:00
Project Finish | 2026-05-17T00:00:00
Total Duration | 482 days
Generated | 2026-02-16 15:37:11
Phase Summary | Task Count
Architecture | 10
MEP Final | 2
Superstructure | 5
Unknown | 10
Discipline Summary | Task Count
ARC | 16
MEP | 8
STR | 3

## BIM 5D Dashboard
Terminal 1 Construction - BIM 5D Analytics Dashboard
Phase Duration Analysis
Phase | Total Days
Unknown | 88.1
Architecture | 15.23
MEP Final | 10.5
Superstructure | 5
Resource Workload Analysis
Phase | Total Man-Days
Unknown | 176.2
Architecture | 36.3
Superstructure | 26
MEP Final | 21
S-Curve Progress Analysis
Week | Cumulative %
W0 | 0
W3 | 44.4
W6 | 63
W9 | 63
W12 | 63
W15 | 63
W18 | 63
W21 | 63
W24 | 63
W27 | 63
W30 | 63
W33 | 63
W36 | 63
W39 | 63
W42 | 63
W45 | 63
W48 | 63
W51 | 63
W54 | 63
W57 | 63
W60 | 63
W63 | 63
W66 | 63
Milestone Timeline | 81.5
Milestone | Day Offset | Date
🏁 Project Start | 0 | 2025-01-21T00:00:00
▶ Superstructure Start | 0 | 2025-01-21T00:00:00
◀ Superstructure End | 7 | 2025-01-28T00:00:00
▶ Architecture Start | 15 | 2025-02-05T00:00:00
◀ Architecture End | 24 | 2025-02-14T00:00:00
▶ MEP Final Start | 30 | 2025-02-20T00:00:00
◀ MEP Final End | 38 | 2025-02-28T00:00:00
▶ Unknown Start | 480 | 2026-05-16T00:00:00
🏁 Project Finish | 481 | 2026-05-17T00:00:00
◀ Unknown End | 512 | 2026-06-17T00:00:00
Gantt Timeline (Strategic Tasks by Phase)
Task | Phase | Start (Day) | Duration (Days)
Level 1 - Install Beam (STR) | Superstructure | 0 | 1
Level 2 - Install Window (ARC) | Architecture | 20 | 3.6
Level 1 - Install FlowTerminal (MEP | MEP Final | 30 | 6.2
Level 2 - Install FlowSegment (MEP) | Unknown | 480 | 26.3
Level 1 - Install FlowFitting (MEP) | Unknown | 480 | 26
Level 1 - Install FlowSegment (MEP) | Unknown | 480 | 16.3
Level 2 - Install FlowFitting (MEP) | Unknown | 480 | 9.4