## Construction Schedule
WBS | Task Name | Phase | Discipline | Storey | Quantity | UOM | Productivity | Duration (days) | Start Date | Finish Date | Labor Resource | Crew Size | Equipment | Status | % Complete
1.2.2 | Ground - Install Column (STR) | Superstructure | STR | Ground | 4 | EA | 6 | 1 | 2025-01-16T00:00:00 | 2025-01-17T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.2.21 | Roof - Install Column (STR) | Superstructure | STR | Roof | 8 | EA | 6 | 1.3333 | 2025-01-16T00:00:00 | 2025-01-18T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.2.156 | Typical_F2 - Install Column (STR) | Superstructure | STR | Typical_F2 | 6 | EA | 6 | 1 | 2025-01-16T00:00:00 | 2025-01-17T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.1 | Ground - Install Beam (STR) | Superstructure | STR | Ground | 22 | EA | 8 | 2.75 | 2025-01-21T00:00:00 | 2025-01-24T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.20 | Roof - Install Beam (STR) | Superstructure | STR | Roof | 2 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.35 | Typical_F10 - Install Beam (STR) | Superstructure | STR | Typical_F10 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.50 | Typical_F11 - Install Beam (STR) | Superstructure | STR | Typical_F11 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.65 | Typical_F12 - Install Beam (STR) | Superstructure | STR | Typical_F12 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.80 | Typical_F13 - Install Beam (STR) | Superstructure | STR | Typical_F13 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.95 | Typical_F14 - Install Beam (STR) | Superstructure | STR | Typical_F14 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.110 | Typical_F15 - Install Beam (STR) | Superstructure | STR | Typical_F15 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.125 | Typical_F16 - Install Beam (STR) | Superstructure | STR | Typical_F16 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.140 | Typical_F17 - Install Beam (STR) | Superstructure | STR | Typical_F17 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.155 | Typical_F2 - Install Beam (STR) | Superstructure | STR | Typical_F2 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.171 | Typical_F3 - Install Beam (STR) | Superstructure | STR | Typical_F3 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.186 | Typical_F4 - Install Beam (STR) | Superstructure | STR | Typical_F4 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.201 | Typical_F5 - Install Beam (STR) | Superstructure | STR | Typical_F5 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.216 | Typical_F6 - Install Beam (STR) | Superstructure | STR | Typical_F6 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.231 | Typical_F7 - Install Beam (STR) | Superstructure | STR | Typical_F7 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.246 | Typical_F8 - Install Beam (STR) | Superstructure | STR | Typical_F8 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.3.261 | Typical_F9 - Install Beam (STR) | Superstructure | STR | Typical_F9 | 4 | EA | 8 | 1 | 2025-01-21T00:00:00 | 2025-01-22T00:00:00 | STEEL_ERECTOR | 4 | MOBILE_CRANE_20T | Not Started | 0
1.4.13 | Ground - Install Slab (STR) | Superstructure | STR | Ground | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.32 | Roof - Install Slab (STR) | Superstructure | STR | Roof | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.46 | Typical_F10 - Install Slab (STR) | Superstructure | STR | Typical_F10 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.61 | Typical_F11 - Install Slab (STR) | Superstructure | STR | Typical_F11 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.76 | Typical_F12 - Install Slab (STR) | Superstructure | STR | Typical_F12 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.91 | Typical_F13 - Install Slab (STR) | Superstructure | STR | Typical_F13 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.106 | Typical_F14 - Install Slab (STR) | Superstructure | STR | Typical_F14 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.121 | Typical_F15 - Install Slab (STR) | Superstructure | STR | Typical_F15 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.136 | Typical_F16 - Install Slab (STR) | Superstructure | STR | Typical_F16 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.151 | Typical_F17 - Install Slab (STR) | Superstructure | STR | Typical_F17 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.167 | Typical_F2 - Install Slab (STR) | Superstructure | STR | Typical_F2 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.182 | Typical_F3 - Install Slab (STR) | Superstructure | STR | Typical_F3 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.197 | Typical_F4 - Install Slab (STR) | Superstructure | STR | Typical_F4 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.212 | Typical_F5 - Install Slab (STR) | Superstructure | STR | Typical_F5 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.227 | Typical_F6 - Install Slab (STR) | Superstructure | STR | Typical_F6 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.242 | Typical_F7 - Install Slab (STR) | Superstructure | STR | Typical_F7 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.257 | Typical_F8 - Install Slab (STR) | Superstructure | STR | Typical_F8 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.4.272 | Typical_F9 - Install Slab (STR) | Superstructure | STR | Typical_F9 | 1 | EA | 35 | 1 | 2025-01-26T00:00:00 | 2025-01-28T00:00:00 | CONCRETE_GANG | 6 | CONCRETE_PUMP | Not Started | 0
1.5.10 | Ground - Install PipeFitting (FP) | MEP Rough-in | FP | Ground | 28 | EA | 15 | 1.8667 | 2025-01-31T00:00:00 | 2025-02-02T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.11 | Ground - Install PipeSegment (FP) | MEP Rough-in | FP | Ground | 23 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.28 | Roof - Install PipeFitting (FP) | MEP Rough-in | FP | Roof | 8 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.29 | Roof - Install PipeSegment (FP) | MEP Rough-in | FP | Roof | 11 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.43 | Typical_F10 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F10 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.44 | Typical_F10 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F10 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.58 | Typical_F11 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F11 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.59 | Typical_F11 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F11 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.73 | Typical_F12 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F12 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.74 | Typical_F12 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F12 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.88 | Typical_F13 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F13 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.89 | Typical_F13 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F13 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.103 | Typical_F14 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F14 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.104 | Typical_F14 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F14 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.118 | Typical_F15 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F15 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.119 | Typical_F15 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F15 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.133 | Typical_F16 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F16 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.134 | Typical_F16 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F16 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.148 | Typical_F17 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F17 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.149 | Typical_F17 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F17 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.164 | Typical_F2 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F2 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.165 | Typical_F2 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F2 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.179 | Typical_F3 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F3 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.180 | Typical_F3 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F3 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.194 | Typical_F4 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F4 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.195 | Typical_F4 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F4 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.209 | Typical_F5 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F5 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.210 | Typical_F5 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F5 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.224 | Typical_F6 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F6 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.225 | Typical_F6 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F6 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.239 | Typical_F7 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F7 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.240 | Typical_F7 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F7 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.254 | Typical_F8 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F8 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.255 | Typical_F8 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F8 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.269 | Typical_F9 - Install PipeFitting (FP) | MEP Rough-in | FP | Typical_F9 | 12 | EA | 15 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.5.270 | Typical_F9 - Install PipeSegment (FP) | MEP Rough-in | FP | Typical_F9 | 13 | EA | 25 | 1 | 2025-01-31T00:00:00 | 2025-02-01T00:00:00 | PLUMBER | 2 |  | Not Started | 0
1.7.3 | Ground - Install Door (ARC) | Architecture | ARC | Ground | 12 | EA | 5 | 2.4 | 2025-02-10T00:00:00 | 2025-02-13T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.16 | Ground - Install StairFlight (ARC) | Architecture | ARC | Ground | 2 | EA | 2 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.18 | Ground - Install Window (ARC) | Architecture | ARC | Ground | 10 | EA | 5 | 2 | 2025-02-10T00:00:00 | 2025-02-12T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.22 | Roof - Install Door (ARC) | Architecture | ARC | Roof | 2 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.36 | Typical_F10 - Install Door (ARC) | Architecture | ARC | Typical_F10 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.51 | Typical_F11 - Install Door (ARC) | Architecture | ARC | Typical_F11 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.66 | Typical_F12 - Install Door (ARC) | Architecture | ARC | Typical_F12 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.81 | Typical_F13 - Install Door (ARC) | Architecture | ARC | Typical_F13 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.96 | Typical_F14 - Install Door (ARC) | Architecture | ARC | Typical_F14 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.111 | Typical_F15 - Install Door (ARC) | Architecture | ARC | Typical_F15 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.126 | Typical_F16 - Install Door (ARC) | Architecture | ARC | Typical_F16 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.141 | Typical_F17 - Install Door (ARC) | Architecture | ARC | Typical_F17 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.157 | Typical_F2 - Install Door (ARC) | Architecture | ARC | Typical_F2 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.172 | Typical_F3 - Install Door (ARC) | Architecture | ARC | Typical_F3 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.187 | Typical_F4 - Install Door (ARC) | Architecture | ARC | Typical_F4 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.202 | Typical_F5 - Install Door (ARC) | Architecture | ARC | Typical_F5 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.217 | Typical_F6 - Install Door (ARC) | Architecture | ARC | Typical_F6 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.232 | Typical_F7 - Install Door (ARC) | Architecture | ARC | Typical_F7 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.247 | Typical_F8 - Install Door (ARC) | Architecture | ARC | Typical_F8 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.7.262 | Typical_F9 - Install Door (ARC) | Architecture | ARC | Typical_F9 | 4 | EA | 5 | 1 | 2025-02-10T00:00:00 | 2025-02-11T00:00:00 | CARPENTER | 2 |  | Not Started | 0
1.8.31 | Roof - Install Roof (ARC) | Architecture | ARC | Roof | 1 | EA | 25 | 1 | 2025-02-15T00:00:00 | 2025-02-16T00:00:00 | ROOFER | 2 |  | Not Started | 0
1.9.7 | Ground - Install LightFixture (ELEC) | MEP Final | ELEC | Ground | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.9 | Ground - Install Outlet (ELEC) | MEP Final | ELEC | Ground | 6 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.26 | Roof - Install LightFixture (ELEC) | MEP Final | ELEC | Roof | 3 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.40 | Typical_F10 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F10 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.42 | Typical_F10 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F10 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.55 | Typical_F11 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F11 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.57 | Typical_F11 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F11 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.70 | Typical_F12 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F12 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.72 | Typical_F12 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F12 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.85 | Typical_F13 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F13 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.87 | Typical_F13 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F13 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.100 | Typical_F14 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F14 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.102 | Typical_F14 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F14 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.115 | Typical_F15 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F15 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.117 | Typical_F15 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F15 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.130 | Typical_F16 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F16 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.132 | Typical_F16 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F16 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.145 | Typical_F17 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F17 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.147 | Typical_F17 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F17 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.161 | Typical_F2 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F2 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.163 | Typical_F2 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F2 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.176 | Typical_F3 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F3 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.178 | Typical_F3 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F3 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.191 | Typical_F4 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F4 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.193 | Typical_F4 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F4 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.206 | Typical_F5 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F5 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.208 | Typical_F5 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F5 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.221 | Typical_F6 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F6 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.223 | Typical_F6 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F6 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.236 | Typical_F7 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F7 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.238 | Typical_F7 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F7 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.251 | Typical_F8 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F8 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.253 | Typical_F8 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F8 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.266 | Typical_F9 - Install LightFixture (ELEC) | MEP Final | ELEC | Typical_F9 | 5 | EA | 20 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.9.268 | Typical_F9 - Install Outlet (ELEC) | MEP Final | ELEC | Typical_F9 | 1 | EA | 25 | 1 | 2025-02-20T00:00:00 | 2025-02-21T00:00:00 | ELECTRICIAN | 2 |  | Not Started | 0
1.11.6 | Ground - Install Furniture (ARC) | Finishes | ARC | Ground | 56 | EA | 8 | 7 | 2025-03-02T00:00:00 | 2025-03-11T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.25 | Roof - Install Furniture (ARC) | Finishes | ARC | Roof | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.39 | Typical_F10 - Install Furniture (ARC) | Finishes | ARC | Typical_F10 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.54 | Typical_F11 - Install Furniture (ARC) | Finishes | ARC | Typical_F11 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.69 | Typical_F12 - Install Furniture (ARC) | Finishes | ARC | Typical_F12 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.84 | Typical_F13 - Install Furniture (ARC) | Finishes | ARC | Typical_F13 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.99 | Typical_F14 - Install Furniture (ARC) | Finishes | ARC | Typical_F14 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.114 | Typical_F15 - Install Furniture (ARC) | Finishes | ARC | Typical_F15 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.129 | Typical_F16 - Install Furniture (ARC) | Finishes | ARC | Typical_F16 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.144 | Typical_F17 - Install Furniture (ARC) | Finishes | ARC | Typical_F17 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.160 | Typical_F2 - Install Furniture (ARC) | Finishes | ARC | Typical_F2 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.175 | Typical_F3 - Install Furniture (ARC) | Finishes | ARC | Typical_F3 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.190 | Typical_F4 - Install Furniture (ARC) | Finishes | ARC | Typical_F4 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.205 | Typical_F5 - Install Furniture (ARC) | Finishes | ARC | Typical_F5 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.220 | Typical_F6 - Install Furniture (ARC) | Finishes | ARC | Typical_F6 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.235 | Typical_F7 - Install Furniture (ARC) | Finishes | ARC | Typical_F7 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.250 | Typical_F8 - Install Furniture (ARC) | Finishes | ARC | Typical_F8 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.11.265 | Typical_F9 - Install Furniture (ARC) | Finishes | ARC | Typical_F9 | 16 | EA | 8 | 2 | 2025-03-02T00:00:00 | 2025-03-05T00:00:00 | FINISHER | 2 |  | Not Started | 0
1.99.0 | Ground - Install AirTerminal (ACMV) | Unknown | ACMV | Ground | 40 | EA | 10 | 4 | 2026-05-16T00:00:00 | 2026-05-21T00:00:00 |  | 2 |  | Not Started | 0
1.99.4 | Ground - Install Fan (STR) | Unknown | STR | Ground | 14 | EA | 10 | 1.4 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.5 | Ground - Install FireSuppressionTerminal (FP) | Unknown | FP | Ground | 14 | EA | 10 | 1.4 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.8 | Ground - Install Member (STR) | Unknown | STR | Ground | 80 | EA | 10 | 8 | 2026-05-16T00:00:00 | 2026-05-26T00:00:00 |  | 2 |  | Not Started | 0
1.99.12 | Ground - Install Plate (ARC) | Unknown | ARC | Ground | 27 | EA | 10 | 2.7 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.14 | Ground - Install Space (STR) | Unknown | STR | Ground | 8 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.15 | Ground - Install Stair (STR) | Unknown | STR | Ground | 2 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.17 | Ground - Install SwitchingDevice (ELEC) | Unknown | ELEC | Ground | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.19 | Roof - Install AirTerminal (ACMV) | Unknown | ACMV | Roof | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.23 | Roof - Install Fan (STR) | Unknown | STR | Roof | 4 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.24 | Roof - Install FireSuppressionTerminal (FP) | Unknown | FP | Roof | 4 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.27 | Roof - Install Member (STR) | Unknown | STR | Roof | 20 | EA | 10 | 2 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.30 | Roof - Install Plate (ARC) | Unknown | ARC | Roof | 8 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.33 | Roof - Install Space (STR) | Unknown | STR | Roof | 4 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.34 | Typical_F10 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F10 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.37 | Typical_F10 - Install Fan (STR) | Unknown | STR | Typical_F10 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.38 | Typical_F10 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F10 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.41 | Typical_F10 - Install Member (STR) | Unknown | STR | Typical_F10 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.45 | Typical_F10 - Install Plate (ARC) | Unknown | ARC | Typical_F10 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.47 | Typical_F10 - Install Space (STR) | Unknown | STR | Typical_F10 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.48 | Typical_F10 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F10 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.49 | Typical_F11 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F11 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.52 | Typical_F11 - Install Fan (STR) | Unknown | STR | Typical_F11 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.53 | Typical_F11 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F11 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.56 | Typical_F11 - Install Member (STR) | Unknown | STR | Typical_F11 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.60 | Typical_F11 - Install Plate (ARC) | Unknown | ARC | Typical_F11 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.62 | Typical_F11 - Install Space (STR) | Unknown | STR | Typical_F11 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.63 | Typical_F11 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F11 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.64 | Typical_F12 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F12 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.67 | Typical_F12 - Install Fan (STR) | Unknown | STR | Typical_F12 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.68 | Typical_F12 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F12 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.71 | Typical_F12 - Install Member (STR) | Unknown | STR | Typical_F12 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.75 | Typical_F12 - Install Plate (ARC) | Unknown | ARC | Typical_F12 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.77 | Typical_F12 - Install Space (STR) | Unknown | STR | Typical_F12 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.78 | Typical_F12 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F12 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.79 | Typical_F13 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F13 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.82 | Typical_F13 - Install Fan (STR) | Unknown | STR | Typical_F13 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.83 | Typical_F13 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F13 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.86 | Typical_F13 - Install Member (STR) | Unknown | STR | Typical_F13 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.90 | Typical_F13 - Install Plate (ARC) | Unknown | ARC | Typical_F13 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.92 | Typical_F13 - Install Space (STR) | Unknown | STR | Typical_F13 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.93 | Typical_F13 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F13 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.94 | Typical_F14 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F14 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.97 | Typical_F14 - Install Fan (STR) | Unknown | STR | Typical_F14 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.98 | Typical_F14 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F14 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.101 | Typical_F14 - Install Member (STR) | Unknown | STR | Typical_F14 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.105 | Typical_F14 - Install Plate (ARC) | Unknown | ARC | Typical_F14 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.107 | Typical_F14 - Install Space (STR) | Unknown | STR | Typical_F14 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.108 | Typical_F14 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F14 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.109 | Typical_F15 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F15 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.112 | Typical_F15 - Install Fan (STR) | Unknown | STR | Typical_F15 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.113 | Typical_F15 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F15 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.116 | Typical_F15 - Install Member (STR) | Unknown | STR | Typical_F15 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.120 | Typical_F15 - Install Plate (ARC) | Unknown | ARC | Typical_F15 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.122 | Typical_F15 - Install Space (STR) | Unknown | STR | Typical_F15 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.123 | Typical_F15 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F15 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.124 | Typical_F16 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F16 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.127 | Typical_F16 - Install Fan (STR) | Unknown | STR | Typical_F16 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.128 | Typical_F16 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F16 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.131 | Typical_F16 - Install Member (STR) | Unknown | STR | Typical_F16 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.135 | Typical_F16 - Install Plate (ARC) | Unknown | ARC | Typical_F16 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.137 | Typical_F16 - Install Space (STR) | Unknown | STR | Typical_F16 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.138 | Typical_F16 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F16 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.139 | Typical_F17 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F17 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.142 | Typical_F17 - Install Fan (STR) | Unknown | STR | Typical_F17 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.143 | Typical_F17 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F17 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.146 | Typical_F17 - Install Member (STR) | Unknown | STR | Typical_F17 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.150 | Typical_F17 - Install Plate (ARC) | Unknown | ARC | Typical_F17 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.152 | Typical_F17 - Install Space (STR) | Unknown | STR | Typical_F17 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.153 | Typical_F17 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F17 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.154 | Typical_F2 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F2 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.158 | Typical_F2 - Install Fan (STR) | Unknown | STR | Typical_F2 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.159 | Typical_F2 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F2 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.162 | Typical_F2 - Install Member (STR) | Unknown | STR | Typical_F2 | 28 | EA | 10 | 2.8 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.166 | Typical_F2 - Install Plate (ARC) | Unknown | ARC | Typical_F2 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.168 | Typical_F2 - Install Space (STR) | Unknown | STR | Typical_F2 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.169 | Typical_F2 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F2 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.170 | Typical_F3 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F3 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.173 | Typical_F3 - Install Fan (STR) | Unknown | STR | Typical_F3 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.174 | Typical_F3 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F3 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.177 | Typical_F3 - Install Member (STR) | Unknown | STR | Typical_F3 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.181 | Typical_F3 - Install Plate (ARC) | Unknown | ARC | Typical_F3 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.183 | Typical_F3 - Install Space (STR) | Unknown | STR | Typical_F3 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.184 | Typical_F3 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F3 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.185 | Typical_F4 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F4 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.188 | Typical_F4 - Install Fan (STR) | Unknown | STR | Typical_F4 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.189 | Typical_F4 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F4 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.192 | Typical_F4 - Install Member (STR) | Unknown | STR | Typical_F4 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.196 | Typical_F4 - Install Plate (ARC) | Unknown | ARC | Typical_F4 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.198 | Typical_F4 - Install Space (STR) | Unknown | STR | Typical_F4 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.199 | Typical_F4 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F4 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.200 | Typical_F5 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F5 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.203 | Typical_F5 - Install Fan (STR) | Unknown | STR | Typical_F5 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.204 | Typical_F5 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F5 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.207 | Typical_F5 - Install Member (STR) | Unknown | STR | Typical_F5 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.211 | Typical_F5 - Install Plate (ARC) | Unknown | ARC | Typical_F5 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.213 | Typical_F5 - Install Space (STR) | Unknown | STR | Typical_F5 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.214 | Typical_F5 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F5 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.215 | Typical_F6 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F6 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.218 | Typical_F6 - Install Fan (STR) | Unknown | STR | Typical_F6 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.219 | Typical_F6 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F6 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.222 | Typical_F6 - Install Member (STR) | Unknown | STR | Typical_F6 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.226 | Typical_F6 - Install Plate (ARC) | Unknown | ARC | Typical_F6 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.228 | Typical_F6 - Install Space (STR) | Unknown | STR | Typical_F6 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.229 | Typical_F6 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F6 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.230 | Typical_F7 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F7 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.233 | Typical_F7 - Install Fan (STR) | Unknown | STR | Typical_F7 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.234 | Typical_F7 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F7 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.237 | Typical_F7 - Install Member (STR) | Unknown | STR | Typical_F7 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.241 | Typical_F7 - Install Plate (ARC) | Unknown | ARC | Typical_F7 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.243 | Typical_F7 - Install Space (STR) | Unknown | STR | Typical_F7 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.244 | Typical_F7 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F7 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.245 | Typical_F8 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F8 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.248 | Typical_F8 - Install Fan (STR) | Unknown | STR | Typical_F8 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.249 | Typical_F8 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F8 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.252 | Typical_F8 - Install Member (STR) | Unknown | STR | Typical_F8 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.256 | Typical_F8 - Install Plate (ARC) | Unknown | ARC | Typical_F8 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.258 | Typical_F8 - Install Space (STR) | Unknown | STR | Typical_F8 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.259 | Typical_F8 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F8 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.260 | Typical_F9 - Install AirTerminal (ACMV) | Unknown | ACMV | Typical_F9 | 10 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.263 | Typical_F9 - Install Fan (STR) | Unknown | STR | Typical_F9 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.264 | Typical_F9 - Install FireSuppressionTerminal (FP) | Unknown | FP | Typical_F9 | 6 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.267 | Typical_F9 - Install Member (STR) | Unknown | STR | Typical_F9 | 26 | EA | 10 | 2.6 | 2026-05-16T00:00:00 | 2026-05-20T00:00:00 |  | 2 |  | Not Started | 0
1.99.271 | Typical_F9 - Install Plate (ARC) | Unknown | ARC | Typical_F9 | 13 | EA | 10 | 1.3 | 2026-05-16T00:00:00 | 2026-05-19T00:00:00 |  | 2 |  | Not Started | 0
1.99.273 | Typical_F9 - Install Space (STR) | Unknown | STR | Typical_F9 | 5 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0
1.99.274 | Typical_F9 - Install SwitchingDevice (ELEC) | Unknown | ELEC | Typical_F9 | 3 | EA | 10 | 1 | 2026-05-16T00:00:00 | 2026-05-17T00:00:00 |  | 2 |  | Not Started | 0

## Project Summary
Terminal 1 Construction
Database | condo_mid.db
Total Tasks | 275
Project Start | 2025-01-16T00:00:00
Project Finish | 2026-05-17T00:00:00
Total Duration | 487 days
Generated | 2026-02-07 07:26:39
Phase Summary | Task Count
Architecture | 21
Finishes | 18
MEP Final | 35
MEP Rough-in | 36
Superstructure | 39
Unknown | 126
Discipline Summary | Task Count
ACMV | 18
ARC | 57
ELEC | 52
FP | 54
STR | 94

## BIM 5D Dashboard
Terminal 1 Construction - BIM 5D Analytics Dashboard
Phase Duration Analysis
Phase | Total Days
Unknown | 170.1
Superstructure | 41.08
Finishes | 41
MEP Rough-in | 36.87
MEP Final | 35
Architecture | 23.4
Resource Workload Analysis
Phase | Total Man-Days
Unknown | 340.2
Superstructure | 200.3
Finishes | 82
MEP Rough-in | 73.7
MEP Final | 70
Architecture | 46.8
S-Curve Progress Analysis
Week | Cumulative %
W0 | 0
W3 | 27.3
W6 | 47.6
W9 | 54.2
W12 | 54.2
W15 | 54.2
W18 | 54.2
W21 | 54.2
W24 | 54.2
W27 | 54.2
W30 | 54.2
W33 | 54.2
W36 | 54.2
W39 | 54.2
W42 | 54.2
W45 | 54.2
W48 | 54.2
W51 | 54.2
W54 | 54.2
W57 | 54.2
W60 | 54.2
W63 | 54.2
W66 | 54.2
Milestone Timeline | 54.2
Milestone | Day Offset | Date
🏁 Project Start | 0 | 2025-01-16T00:00:00
▶ Superstructure Start | 0 | 2025-01-16T00:00:00
◀ Superstructure End | 12 | 2025-01-28T00:00:00
▶ MEP Rough-in Start | 15 | 2025-01-31T00:00:00
◀ MEP Rough-in End | 17 | 2025-02-02T00:00:00
▶ Architecture Start | 25 | 2025-02-10T00:00:00
◀ Architecture End | 31 | 2025-02-16T00:00:00
▶ MEP Final Start | 35 | 2025-02-20T00:00:00
◀ MEP Final End | 36 | 2025-02-21T00:00:00
▶ Finishes Start | 45 | 2025-03-02T00:00:00
◀ Finishes End | 54 | 2025-03-11T00:00:00
▶ Unknown Start | 485 | 2026-05-16T00:00:00
🏁 Project Finish | 486 | 2026-05-17T00:00:00
◀ Unknown End | 495 | 2026-05-26T00:00:00
Gantt Timeline (Strategic Tasks by Phase)
Task | Phase | Start (Day) | Duration (Days)
Ground - Install Beam (STR) | Superstructure | 5 | 2.8
Ground - Install PipeFitting (FP) | MEP Rough-in | 15 | 1.9
Ground - Install Door (ARC) | Architecture | 25 | 2.4
Ground - Install LightFixture (ELEC | MEP Final | 35 | 1
Ground - Install Furniture (ARC) | Finishes | 45 | 7
Ground - Install Member (STR) | Unknown | 485 | 8
Ground - Install AirTerminal (ACMV) | Unknown | 485 | 4
Typical_F2 - Install Member (STR) | Unknown | 485 | 2.8